Here is the detailed breakdown for Phase 8: Project Demonstration Phase, specifically written and structured for your Script-Controlled ACL – Restrict Record Access Based on Field Value implementation in Microsoft Project.

Copy-Paste for Microsoft Project

Copy the text inside the box below and paste it directly into the Task Name column in MS Project under your Phase 8 section:

Plaintext

Project Demonstration Phase

Prepare test records across all target field values (e.g., Draft, Confidential, Restrict)

Configure test user personas (Authorized vs Unauthorized roles) for live switching

Draft Demonstration Script and agenda covering end-to-end access scenarios

Verify environment stability and confirm ACL cache refresh in target demo instance

Execute live demonstration of Script-Controlled ACL behavior to stakeholders

Demonstrate negative test cases (access denied when field value changes)

Demonstrate positive test cases (access granted when field value matches criteria)

Review Technical Design Document (TDD) and Security Matrix with audit/security team

Address stakeholder questions, feedback, and edge-case queries

Obtain formal demonstration sign-off and approval for production deployment

MS Project Detailed Task Matrix

| Task ID | Task Name | Duration | Predecessors | Key Deliverable / Objective |
| --- | --- | --- | --- | --- |
| 8.0 | Project Demonstration Phase | 3 days | 6, 7 | Executive & Technical Walkthrough |
| 8.1 | Prepare test records across field values | 0.5 days | 6FS, 7FS | Representative sample data set |
| 8.2 | Configure test user personas | 0.5 days | 8.1 | Demo accounts (Impersonation ready) |
| 8.3 | Draft Demonstration Script and agenda | 0.5 days | 8.2 | Step-by-step presentation outline |
| 8.4 | Verify environment stability & clear ACL cache | 0.25 days | 8.3 | Demo instance readiness |
| 8.5 | Execute live demonstration to stakeholders | 0.25 days | 8.4 | Live presentation |
| 8.6 | Demonstrate negative test cases (Access Denied) | In 8.5 | — | Unauthorized view/read rejection |
| 8.7 | Demonstrate positive test cases (Access Granted) | In 8.5 | — | Field-level access validation |
| 8.8 | Review TDD and Security Matrix with audit team | 0.5 days | 8.5 | Compliance verification |
| 8.9 | Address stakeholder feedback & queries | 0.25 days | 8.8 | Action item resolution |
| 8.10 | Obtain formal deployment sign-off | 0 days (Milestone) | 8.9 | Prod Go-Live Authorization |

Recommended MS Project Setup Notes

- Milestone: Set Task 8.10 duration to 0d so MS Project renders it as a Milestone Diamond on your Gantt chart.

- Dependencies: Link Phase 8 to start only after Phase 6 (Testing) and Phase 7 (Documentation) are 100% complete (6FS, 7FS).